## Sheet1
User Story ID | User Story | Priority | Front End Scrum Points | Back End Scrum Points | Alana | Alex | Daniel | Gleb | Estimated Duration
1 | As a user (logged-in/logged-out), I want to be able to view a basic contact page, so that I can find information on how to contact the company. | Normal | 1 | 1 | 2 | 1 | 0.5 | 0.5 | 0.5
2 | As a user (logged-in/logged-out), I want to be able to view a basic home page, so that I can access all the functionalities of the website | Urgent | 1 | 1 | 1 | 1 | 1 | 1 | 1
3 | As a customer, I want to be able to view a services page, so that I can find a service to book an appointment for. | High | 2 | 2 | 5 | 4 | 4 | 5 | 1
4 | As a customer, I want to register an account for myself, so that I can have access to book an appointment for a service. | Urgent | 3 | 3 | 5 | 4 | 5 | 5 | 2
5 | As the Admin, I want to add employees to the application/database so that I can roster them shifts and add available booking times. | Normal | 4 | 3 | 4 | 3 | 4 | 4 | 3
6 | As the Admin, I want to roster employees shifts so that I can add booking times for customers to book a certain service with an employee | Normal | 3 | 3 | 5 | 4 | 5 | 4 | 4
7 | As a customer, I want to search for a service and its available time slots, so that I can book a time suitable for me. | Normal | 3 | 3 | 5 | 4 | 3 | 3 | 6
8 | As a customer, I want to look up a service and the worker/s allocated to it, so that I can decide whether or not I want to book the service. | Normal | 4 | 4 | 5 | 4 | 4 | 4 | 8
9 | As a customer, I want to book a specific worker for a specific service, so that I can ensure that the quality of the service is adequate. | High | 4 | 4 | 5 | 2 | 5 | 5 | 5
10 | As a customer, I want to book a service on a specific date, so that the service is completed on a day that is suitable for me. | Normal | 2 | 4 | 2 | 3 | 1 | 1 | 4
11 | As a customer, I want to edit my address on my customer profile page, so that my details are accurate and up to date. | Normal | 1 | 1 | 3 | 4 | 3 | 3 | 2
12 | As a customer, I want to change my password on my customer profile page, so that my account is secure. | Normal | 1 | 1 | 4 | 3 | 2 | 1 | 2
13 | As a customer, I want to cancel a booking, so that I can book an appointment for another day. | High | 1 | 3 | 4 | 2 | 2 | 2 | 5
14 | As a customer, I want to display a history of my bookings, so that I can search if a service has been completed recently. | High | 2 | 3 | 4 | 4 | 2 | 2 | 4
15 | As a worker, I want to view my profile, so that I can view the services I am providing and the dates I am providing them. | Low priority | 3 | 3 | 4 | 4 | 4 | 4 | 6
16 | As a worker, I want to view my assigned working hours/days, so that I can determine which days I am free. | Low priority | 2 | 2 | 4 | 3 | 4 | 4 | 4
17 | As a user(logged-in/logged-out), I want to view my account page, so that I may check the permissions that I have | Urgent | 4 | 4 | 4 | 3 | 4 | 4 | 6
18 | As a user(logged-in/logged-out), I want to see the company’s email address, so that I may send them emails about booking enquiries. | Urgent | 2 | 1 | 1 | 1 | 1 | 1 | 2
19 | As a user(logged-in/logged-out), I want to contact the company via telephone, so that I may enquire about booking issues I may have. | Normal | 2 | 1 | 1 | 1 | 1 | 1 | 2
20 | As an admin, I want to be able to view statistic pages, so that I get some insights about the past bookings, new bookings, cancelled bookings. | Low priority | 4 | 4 | 5 | 5 | 5 | 5 | 8